## Project Overview
Parameter | Value | Notes
Project Start | 2025-01-15
Planned End Date | 2025-05-15
Projected End Date | 2025-06-05 | Based on current burndown rate
Total Budget | 3000000 | USD
Spent | 750000 | USD
Remaining | 750000 | USD
Overrun Risk | Medium
Total Hours Allocated | 2560
Total Hours Used | 2080
Hours Remaining | 735
Percent Complete | 71.3%
Burndown Rate | 141.15 | Hours per week
Estimated Weeks Remaining | 5.2

## Weekly Hours
Week Ending | Planned Hours | Actual Hours | Cumulative Planned | Cumulative Actual | Hours Variance
2025-01-24 | 160 | 155 | 160 | 155 | -5
2025-01-31 | 160 | 158 | 320 | 313 | -2
2025-02-07 | 160 | 152 | 480 | 465 | -8
2025-02-14 | 160 | 150 | 640 | 615 | -10
2025-02-21 | 160 | 155 | 800 | 770 | -5
2025-02-28 | 160 | 150 | 960 | 920 | -10
2025-03-07 | 160 | 140 | 1120 | 1060 | -20
2025-03-14 | 160 | 145 | 1280 | 1205 | -15
2025-03-21 | 160 | 150 | 1440 | 1355 | -10
2025-03-28 | 160 | 155 | 1600 | 1510 | -5
2025-04-04 | 160 | 160 | 1760 | 1670 | 0
2025-04-11 | 160 | 155 | 1920 | 1825 | -5
2025-04-18 | 160 | 0 | 2080 | 1825 | -160
2025-04-25 | 160 | 0 | 2240 | 1825 | -160
2025-05-02 | 160 | 0 | 2400 | 1825 | -160
2025-05-09 | 160 | 0 | 2560 | 1825 | -160

## Task Completion
Task | Planned % | Actual % | Variance
Foundation | 100 | 100 | 0
Framing | 80 | 75 | -5
MEP | 60 | 45 | -15
Finishes | 30 | 20 | -10

## Issues
Date | System | Issue | Impact | Accountability | Consequence
2025-04-10 | MEP | HVAC routing conflict | 2-day delay | Contractor | Schedule adjustment needed
2025-04-08 | Structural | Steel delivery delay | 3-day delay | Supplier | Additional crew scheduling